## Slide 1
Development of a Python-Based
Interface for a PXI Data
Acquisition System
Bachelor Project (6 ECTS) — Introduction Presentation
Samir Elsherbiny
Matrikel-Nr. 5581873
Supervisors: Prof. Dr. Oliver Amft, Dr. Mohammad Amayreh
IESLab, University of Freiburg | Hahn-Schickard
27 April 2026

## Slide 2
What is a DAQ / PXI System?
Data Acquisition (DAQ)
Converts real-world analog signals into digital data a computer can process
Key functions:
Measure voltage, current, temperature
Generate analog/digital output signals
Synchronize multiple channels
High-speed sampling (MHz range)
PXI (PCI eXtensions for Instrumentation)
Modular, high-performance platform by National Instruments
Advantages over USB DAQ:
Higher bandwidth & lower latency
Up to 14 MS/s per channel
Hardware synchronization
Scalable: add more cards as needed
This project: PXI system with 2 analog input cards (8 ch each, 14 MS/s) + 1 analog out / digital I/O card

## Slide 3
Project Goal & Work Packages
Goal: Develop a Python-based software interface for reliable analog signal acquisition and output control on a PXI system
WP1
Hardware & DAQ Concepts
Learn DAQ fundamentals, compare USB/PCI/PXI
WP2
NI Python API
Read analog inputs, generate outputs, explore triggers
WP3
Real-Time Visualization
Live plotting, multithreading, prevent buffer overflow
WP4
Validation & Experiments
Test with function generators & oscilloscopes
WP5
Documentation & Report
LaTeX report, code documentation, presentation

## Slide 4
Timeline & Approach
WP1
Week 1-2
Learn & Explore
WP2
Week 3-5
API & Coding
WP3
Week 5-8
Real-Time SW
WP4
Week 8-10
Experiments
WP5
Week 3-14
Report (ongoing)
Key Milestones
27 Apr 2026
Project Start & Introduction Presentation
27 Jul 2026
Report Submission Deadline
15 Aug 2026
Final Presentation (20 min)
Technical Approach
Python + NI-DAQmx API for hardware control
Multithreading / multiprocessing for real-time performance
Reference: Ahmad Ahmad's thesis (similar GUI + DAQ project)

## Slide 5
Thank You
Questions?
Samir Elsherbiny | samir.elsherbiny@students.uni-freiburg.de
IESLab, University of Freiburg | Hahn-Schickard