## GANTT Chart
# | Task / Work Package | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
|  |  |  | 27 Apr | 04 May | 11 May | 18 May | 25 May | 01 Jun | 08 Jun | 15 Jun | 22 Jun | 29 Jun | 06 Jul | 13 Jul | 20 Jul | 27 Jul | 03 Aug | 10 Aug
WP1: Familiarization with Hardware & DAQ
1.1 | Learn DAQ fundamentals (videos, reading) | 27 Apr | 04 May | bar: 27 Apr to 04 May
1.2 | Compare USB vs PCI vs PXI systems | 04 May | 10 May | bar: 04 May to 11 May
1.3 | Study PXI system hardware at Hahn-Schickard | 27 Apr | 10 May | bar: 27 Apr to 11 May
★ | MILESTONE: Introduction Presentation (27 Apr) | 27 Apr | 27 Apr | bar: 27 Apr
WP2: NI Python API Investigation
2.1 | Install NI-DAQmx drivers + nidaqmx Python | 11 May | 17 May | bar: 11 May to 18 May
2.2 | Analog input: single & multi-channel read | 11 May | 24 May | bar: 11 May to 25 May
2.3 | Max sampling rate experiments | 18 May | 24 May | bar: 18 May to 25 May
2.4 | Waveform generation (sine, square, ramp) | 18 May | 31 May | bar: 18 May to 01 Jun
2.5 | Explore triggers, timers, interrupts | 25 May | 07 Jun | bar: 25 May to 08 Jun
WP3: Real-Time Acquisition & Visualization
3.1 | Basic acquisition loop + matplotlib test | 01 Jun | 07 Jun | bar: 01 Jun to 08 Jun
3.2 | Implement pyqtgraph real-time plotting | 08 Jun | 14 Jun | bar: 08 Jun to 15 Jun
3.3 | Multithreading: producer-consumer pattern | 08 Jun | 21 Jun | bar: 08 Jun to 22 Jun
3.4 | Multiprocessing experiments | 15 Jun | 21 Jun | bar: 15 Jun to 22 Jun
3.5 | Performance benchmarking & limits analysis | 22 Jun | 28 Jun | bar: 22 Jun to 29 Jun
WP4: Validation & Experiments
4.1 | Connect function generator, verify inputs | 29 Jun | 05 Jul | bar: 29 Jun to 06 Jul
4.2 | Verify PXI output signals on oscilloscope | 29 Jun | 05 Jul | bar: 29 Jun to 06 Jul
4.3 | Long-duration stability tests | 06 Jul | 12 Jul | bar: 06 Jul to 13 Jul
4.4 | Record results: plots, tables, screenshots | 06 Jul | 12 Jul | bar: 06 Jul to 13 Jul
WP5: Documentation & Report
5.1 | Write Introduction + Background (ongoing) | 11 May | 28 Jun | bar: 11 May to 29 Jun
5.2 | Write Implementation chapter | 29 Jun | 12 Jul | bar: 29 Jun to 13 Jul
5.3 | Write Results + Conclusion + Outlook | 06 Jul | 19 Jul | bar: 06 Jul to 20 Jul
5.4 | Final polish, proofread, LaTeX formatting | 13 Jul | 26 Jul | bar: 13 Jul to 27 Jul
★ | MILESTONE: Report Submission (27 Jul) | 27 Jul | 27 Jul | bar: 27 Jul
5.5 | Prepare final presentation slides | 27 Jul | 14 Aug | bar: 27 Jul to 10 Aug
★ | MILESTONE: Final Presentation (15 Aug) | 15 Aug | 15 Aug | bar: 10 Aug